## Cross-Sprint Summary
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
S2-US10 | User Story | Added | Event Suggestions and event/activity recommendations. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 3, 8, 15, 22 | 01_Sprint_2_AI_Report_EN_Final.docx | Sections 4 and 5 | Complete | Body text expands AI business scope and Event Suggestions.
S2-US15 | User Story | Added | Home Page order includes Today Check-in Card, Event Suggestions, Friends Activity, and AI Assistant Entry as the fourth module. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 5, 10, 12, 14 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 3 | Complete | Body text lists the four-module order item by item.
HP-FR4 | Functional Requirement | Added | Home Page optional short prompt may be based on previous mood or today's Check-in status. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 59, 70 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 3 | Complete | Body text states the two permitted sources.
HP-FR7 | Functional Requirement | Added | AI Assistant Entry provides Ask AI for suggestions, Find an activity for me, and What can I do today? | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 60, 70 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 3 | Complete | Body text lists the three prompts.
AR-FR1 | Functional Requirement | Added | Event Suggestions order: AI-supported recommendations; permitted friends Going or Booked externally events; permitted friends Interested events; events matching interests, age group, or region. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 67, 77 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 5 | Complete | Body text lists the four-level order and confirms Going/Booked externally as the second category.
S3-US02-AC1 | Acceptance Criteria | Added | System displays available friend recommendations as recommendation cards. | Sprint 3 | Sprint 2 retained AI safety boundary | Final frozen business requirement | Sprint 3.pdf | 3, 5, 9 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 4 | Complete | Body text states recommendation cards.
S3-US02-AC2 | Acceptance Criteria | Added | Recommendation uses one or more allowed factors: same interests, user-permitted approximate region, shared event interest. | Sprint 3 | Sprint 2 retained AI safety boundary | Final frozen business requirement | Sprint 3.pdf | 3, 27, 33 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 5 | Complete | Body text lists the three permitted factors.
S3-US02-AC3 | Acceptance Criteria | Added | Recommendation card includes avatar, name, grounded recommendation reason, Detail, and Add Friend. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 3, 5, 9 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 4 | Complete | Body text lists card fields.
S3-US02-AC4 | Acceptance Criteria | Added | Recommendation reason corresponds to at least one actual allowed factor used. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 3, 27, 33 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 5 | Complete | Body text states that the reason corresponds to actual factors.
S3-US02-AC5 | Acceptance Criteria | Added | Detail opens existing Profile with permission-based viewer state. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 9, 27, 39 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 4 | Complete | Body text states the Detail rules.
No formal ID / Gemini Provider Decision | Internal Traceability Label | Added technical integration | Gemini is the Sprint 4 historical AI provider; model name/version remains Backend configurable; free allowance is not a production guarantee. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 1 | 03_Sprint_4_AI_Report_EN_Final.docx | Sections 3 and 4 | Complete | Internal label only; not a source PDF formal Requirement ID.
No formal ID / Backend-only Integration | Internal Traceability Label | Added technical integration | Flutter does not call Gemini directly; Backend performs authentication, purpose, input validation, permission, privacy, visibility, retrieval, minimisation, context, adapter invocation, parsing, validation, fallback and return. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 1-2 | 03_Sprint_4_AI_Report_EN_Final.docx | Sections 5, 6, and 11 | Complete | Internal label only; not a source PDF formal Requirement ID.
No formal ID / Response Validation | Internal Traceability Label | Added technical integration | Response validation covers format, fields, identifiers, factors, missing/malformed values, restricted information, unsupported claims, purpose mismatch and unknown objects. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 2-3 | 03_Sprint_4_AI_Report_EN_Final.docx | Section 8 | Complete | Internal label only; not a source PDF formal Requirement ID.
No formal ID / Failure and Fallback | Internal Traceability Label | Added technical integration | Fallback covers timeout, network failure, rate limiting, invalid response, missing fields, unsupported output and unavailable Gemini service; retry is bounded. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 2-3 | 03_Sprint_4_AI_Report_EN_Final.docx | Section 9 | Complete | Internal label only; not a source PDF formal Requirement ID.
No formal ID / Logging and Secret Boundary | Internal Traceability Label | Added technical integration | Operational metadata, raw prompt/response retention boundary, AI operational record retention configuration, and secret-management placement. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 3-4 | 03_Sprint_4_AI_Report_EN_Final.docx | Section 10 | Complete | Internal label only; not a source PDF formal Requirement ID.
Supplementary Project Decision / Friend Recommendation Algorithm Boundary | Supplementary Project Decision | Project Rationale | Friend Recommendation uses Backend deterministic rule-based matching and does not call Gemini; this is not a Sprint 4 PDF formal Requirement ID. | Sprint 4 | Sprint 3 business factors plus Sprint 4 Gemini responsibility boundary | Final supplementary project decision | Project Rationale / Supplementary Project Decision | Source text decision | 03_Sprint_4_AI_Report_EN_Final.docx | Sections 15 and 16 | Complete | Separately identified as Supplementary Project Decision.
NIS-CH01 | Change Register | Modified | NIS-CH01 AI Provider and Model Migration Modified and Removed Remove Gemini, Gemini API, Gemini Provider Adapter, Gemini credentials, quota, billing, free-tier, rate-limit, SDK, and cloud-provider dependencies. Adopt Qwen3.5-9B as the primary model and Qwen3.5-4B as the manually configured development and low-spec alternative model | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 2, 23 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-CH02 | Change Register | Modified | NIS-CH02 Local AI Runtime and Backend Integration Modified Use Ollama as the current local inference runtime and Qwen Local Model Adapter as the single Backend integration abstraction. Preserve Backend-only access, data minimisation, validation, deterministic Backend fallback, and no direct model-to-database access | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 2, 23 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-CH03 | Change Register | Added | NIS-CH03 Backend Admin Identity and Access Added Add a manually assigned Admin role using existing Firebase Authentication and Firebase custom claims. Allow a small set of manually approved Admins. All Admin operations require Backend authentication and authorisation | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 2, 23 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC01 | Acceptance Criteria | Modified | NIS-AC01: Qwen3.5-9B shall be the project’s primary model. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 3, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC22 | Acceptance Criteria | Added | NIS-AC22: Final account-state execution semantics, including exact grounds, evidence requirements, distinctions between action types, suspension duration, session handling, user notification, appeal, restoration criteria, deletion meaning and effects, data retention, and cascading data handling, remain Deferred and shall not be inferred in this Sprint. 4. Added and Modified Use Cases 4.1 Added or Consolidated Use Cases | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Deferred | Sprint 5 edit.pdf | 6, 10, 26, 29 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Deferred | Source explicitly defers this scope or execution semantics; target DOCX preserves the deferred status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR17 | Functional Requirement | Added | NIS-FR17 Added The Sprint shall produce a design-level Backend specification for protected User Account Administration preparation covering future Disable, Suspend, Delete, and Restore action types, authorised actors, shared Admin API scope, permitted administrative metadata, validation boundaries, audit fields, rejection behaviour, security restrictions, and an explicit no-account-state-change boundary | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 13, 17, 32, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-UC03 | Use Case | Modified | NIS-UC03 — Prepare a User Account Administration Operation Primary Actor: Admin Preconditions The Admin is authenticated through Firebase Authentication. The Backend verifies the Admin custom claim. The target account can be identified using only permitted minimum administrative account metadata: Firebase UID, account identifier or unique username, username, email address, current account status, and current administrative state. The design specifies that requests use the same shared protected internal Admin API defined for confirmed Interest operations. Trigger The Admin submits a design-level account-administration preparation request | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 9, 28 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.

## Sprint 2
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
S2-US10 | User Story | Added | Event Suggestions and event/activity recommendations. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 3, 8, 15, 22 | 01_Sprint_2_AI_Report_EN_Final.docx | Sections 4 and 5 | Complete | Body text expands AI business scope and Event Suggestions.
S2-US15 | User Story | Added | Home Page order includes Today Check-in Card, Event Suggestions, Friends Activity, and AI Assistant Entry as the fourth module. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 5, 10, 12, 14 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 3 | Complete | Body text lists the four-module order item by item.
HP-FR4 | Functional Requirement | Added | Home Page optional short prompt may be based on previous mood or today's Check-in status. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 59, 70 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 3 | Complete | Body text states the two permitted sources.
HP-FR7 | Functional Requirement | Added | AI Assistant Entry provides Ask AI for suggestions, Find an activity for me, and What can I do today? | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 60, 70 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 3 | Complete | Body text lists the three prompts.
AR-FR1 | Functional Requirement | Added | Event Suggestions order: AI-supported recommendations; permitted friends Going or Booked externally events; permitted friends Interested events; events matching interests, age group, or region. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 67, 77 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 5 | Complete | Body text lists the four-level order and confirms Going/Booked externally as the second category.
AR-FR2 | Functional Requirement | Added | Each event/activity recommendation provides a clear and understandable reason. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 67, 77 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 5 | Complete | Body text states the requirement for each recommendation reason.
AR-FR3 | Functional Requirement | Added | When personalised information is insufficient, return safe fallback recommendation without unsupported recommendation factors. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 67, 77 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 7 | Complete | Body text states fallback and the prohibition against expanding factors.
AIC-FR1 | Functional Requirement | Added | AI Check-in Support may provide lightweight prompt based on previous mood information or today's Check-in status. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 68, 78 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 6 | Complete | Body text states the AI Check-in prompt.
AIC-FR2 | Functional Requirement | Added | AI Check-in Support may use only previous mood information, today's Check-in status, Check-in text, and existing interests when consent/privacy permits. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 68, 78 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 6 | Complete | Body text uses the closed data list.
AIC-NFR1 | Non-functional Requirement | Added | AI Check-in prompts should be short, clear, and understandable. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 68, 78 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 6 | Complete | Body text lists prompt quality requirements.
AS-FR1 | Functional Requirement | Added | AI does not provide medical diagnosis, psychological treatment, legal advice, or emergency response. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 69, 79 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 7 | Complete | Body text lists the four prohibited content categories.
AS-FR2 | Functional Requirement | Added | When request exceeds approved AI scope, return clear boundary response. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 68, 78 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 7 | Complete | Body text states boundary response.
AS-NFR1 | Non-functional Requirement | Added | AI-supported content must stay within approved business scope. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 69, 79 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 7 | Complete | Body text states approved AI scope limits.
AS-NFR2 | Non-functional Requirement | Added | AI must not present as doctor, therapist, lawyer, emergency service, or other professional authority. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | 69, 79 | 01_Sprint_2_AI_Report_EN_Final.docx | Section 7 | Complete | Body text lists the professional authority boundary.
S2-Scope | Scope Note / Business Rule | Added | Check-in location is optional, consent-based and approximate; precise, real-time, continuous and background tracking are not allowed; friend features are out of scope. | Sprint 2 |  | Final frozen business requirement | Sprint 2.pdf | source scope notes | 01_Sprint_2_AI_Report_EN_Final.docx | Sections 8 and 9 | Complete | Body text expands the location boundary and friend-feature out-of-scope boundary.

## Sprint 3
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
S3-US02-AC1 | Acceptance Criteria | Added | System displays available friend recommendations as recommendation cards. | Sprint 3 | Sprint 2 retained AI safety boundary | Final frozen business requirement | Sprint 3.pdf | 3, 5, 9 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 4 | Complete | Body text states recommendation cards.
S3-US02-AC2 | Acceptance Criteria | Added | Recommendation uses one or more allowed factors: same interests, user-permitted approximate region, shared event interest. | Sprint 3 | Sprint 2 retained AI safety boundary | Final frozen business requirement | Sprint 3.pdf | 3, 27, 33 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 5 | Complete | Body text lists the three permitted factors.
S3-US02-AC3 | Acceptance Criteria | Added | Recommendation card includes avatar, name, grounded recommendation reason, Detail, and Add Friend. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 3, 5, 9 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 4 | Complete | Body text lists card fields.
S3-US02-AC4 | Acceptance Criteria | Added | Recommendation reason corresponds to at least one actual allowed factor used. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 3, 27, 33 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 5 | Complete | Body text states that the reason corresponds to actual factors.
S3-US02-AC5 | Acceptance Criteria | Added | Detail opens existing Profile with permission-based viewer state. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 9, 27, 39 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 4 | Complete | Body text states the Detail rules.
S3-US02-AC6 | Acceptance Criteria | Added | Add Friend starts Send Friend Request flow. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 9, 27, 39 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 4 | Complete | Body text states the Add Friend flow.
S3-US02-AC7 | Acceptance Criteria | Added | No permitted recommendation shows user-visible no-recommendations state. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 3, 27, 49 | 02_Sprint_3_AI_Report_EN_Final.docx | Section 4 | Complete | Body text states the no-recommendations state.
S3-UC01 | Use Case | Added | User views recommendation card, opens Detail, and can start Add Friend flow under permissions. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 3, 9, 11, 27 | 02_Sprint_3_AI_Report_EN_Final.docx | Sections 4-5 | Complete | Body text covers the use case.
S3-REC-FR | Functional Requirement | Added | Friend Recommendation functional clauses covering card, allowed factors, Profile Detail and friend request flow. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 20, 27, 49, 56 | 02_Sprint_3_AI_Report_EN_Final.docx | Sections 4-5 | Complete | Body text expands the formal clauses.
S3-REC-NFR | Non-functional Requirement / Scope Note | Added | Privacy, visibility, approximate-region limits, prohibited score/profile/AI confidence/hidden/personality/behavioural/mental-health factors. | Sprint 3 |  | Final frozen business requirement | Sprint 3.pdf | 21, 27, 49, 56 | 02_Sprint_3_AI_Report_EN_Final.docx | Sections 6-8 | Complete | Body text fully lists prohibited factors.

## Sprint 4 Decisions
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
No formal ID / Gemini Provider Decision | Internal Traceability Label | Added technical integration | Gemini is the Sprint 4 historical AI provider; model name/version remains Backend configurable; free allowance is not a production guarantee. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 1 | 03_Sprint_4_AI_Report_EN_Final.docx | Sections 3 and 4 | Complete | Internal label only; not a source PDF formal Requirement ID.
No formal ID / Backend-only Integration | Internal Traceability Label | Added technical integration | Flutter does not call Gemini directly; Backend performs authentication, purpose, input validation, permission, privacy, visibility, retrieval, minimisation, context, adapter invocation, parsing, validation, fallback and return. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 1-2 | 03_Sprint_4_AI_Report_EN_Final.docx | Sections 5, 6, and 11 | Complete | Internal label only; not a source PDF formal Requirement ID.
No formal ID / Response Validation | Internal Traceability Label | Added technical integration | Response validation covers format, fields, identifiers, factors, missing/malformed values, restricted information, unsupported claims, purpose mismatch and unknown objects. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 2-3 | 03_Sprint_4_AI_Report_EN_Final.docx | Section 8 | Complete | Internal label only; not a source PDF formal Requirement ID.
No formal ID / Failure and Fallback | Internal Traceability Label | Added technical integration | Fallback covers timeout, network failure, rate limiting, invalid response, missing fields, unsupported output and unavailable Gemini service; retry is bounded. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 2-3 | 03_Sprint_4_AI_Report_EN_Final.docx | Section 9 | Complete | Internal label only; not a source PDF formal Requirement ID.
No formal ID / Logging and Secret Boundary | Internal Traceability Label | Added technical integration | Operational metadata, raw prompt/response retention boundary, AI operational record retention configuration, and secret-management placement. | Sprint 4 | Sprint 4 source text | Historical but superseded | Sprint 4(1).pdf | 3-4 | 03_Sprint_4_AI_Report_EN_Final.docx | Section 10 | Complete | Internal label only; not a source PDF formal Requirement ID.
Supplementary Project Decision / Friend Recommendation Algorithm Boundary | Supplementary Project Decision | Project Rationale | Friend Recommendation uses Backend deterministic rule-based matching and does not call Gemini; this is not a Sprint 4 PDF formal Requirement ID. | Sprint 4 | Sprint 3 business factors plus Sprint 4 Gemini responsibility boundary | Final supplementary project decision | Project Rationale / Supplementary Project Decision | Source text decision | 03_Sprint_4_AI_Report_EN_Final.docx | Sections 15 and 16 | Complete | Separately identified as Supplementary Project Decision.

## Sprint 5 Change Register
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
NIS-CH01 | Change Register | Modified | NIS-CH01 AI Provider and Model Migration Modified and Removed Remove Gemini, Gemini API, Gemini Provider Adapter, Gemini credentials, quota, billing, free-tier, rate-limit, SDK, and cloud-provider dependencies. Adopt Qwen3.5-9B as the primary model and Qwen3.5-4B as the manually configured development and low-spec alternative model | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 2, 23 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-CH02 | Change Register | Modified | NIS-CH02 Local AI Runtime and Backend Integration Modified Use Ollama as the current local inference runtime and Qwen Local Model Adapter as the single Backend integration abstraction. Preserve Backend-only access, data minimisation, validation, deterministic Backend fallback, and no direct model-to-database access | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 2, 23 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-CH03 | Change Register | Added | NIS-CH03 Backend Admin Identity and Access Added Add a manually assigned Admin role using existing Firebase Authentication and Firebase custom claims. Allow a small set of manually approved Admins. All Admin operations require Backend authentication and authorisation | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 2, 23 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-CH04 | Change Register | Added | NIS-CH04 Interest Administration Added Allow authorised Admins to create, read, update, deactivate, and reactivate Interest content through protected Backend operations. Preserve existing references when an Interest is deactivated and prevent new use of inactive Interests | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 3, 23 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-CH05 | Change Register | Added | NIS-CH05 User Account Administration Preparation Added Formally expand the previously confirmed Admin scope from Interest administration only to Interest administration plus protected User Account Administration design and preparation. Produce a design-level Backend specification covering authorised access, the shared Admin API scope, permitted administrative account metadata, target identification, validation boundaries, audit fields, rejection behaviour, security restrictions, and an explicit no-account-state-change boundary for future Disable, Suspend, Delete, and Restore action types. Final action semantics and account-state effects remai | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 3, 23 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.

## Sprint 5 AC
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
NIS-AC01 | Acceptance Criteria | Modified | NIS-AC01: Qwen3.5-9B shall be the project’s primary model. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 3, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC02 | Acceptance Criteria | Modified | NIS-AC02: Qwen3.5-4B shall be used only as the manually configured development and low-spec alternative model and shall not be presented as a second primary model, an automatic failover model, or a runtime-routing target | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 3, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC03 | Acceptance Criteria | Modified | NIS-AC03: Ollama shall be the current local inference runtime, and the Backend shall communicate with it through Qwen Local Model Adapter. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC04 | Acceptance Criteria | Modified | NIS-AC04: Gemini API, credentials, quotas, billing, free-tier assumptions, provider-specific SDK bindings, and Gemini Provider Adapter shall no longer be required. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC05 | Acceptance Criteria | Modified | NIS-AC05: Existing approved AI explanations, summaries, constrained suggestions, recommendation support, and Persona-based responses shall remain within their previously approved business scope. All recommendation candidates, weights, scores, and final ordering shall be generated by the deterministic Backend recommendation algorithm. Qwen may only explain, summarise, or conversationally present Backend-approved recommendation results and shall not add candidates, modify weights, override scores, or change final ordering. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC06 | Acceptance Criteria | Modified | NIS-AC06: Flutter shall not directly call Qwen3.5-9B, Qwen3.5-4B, Ollama, vLLM, SGLang, llama.cpp, or a model endpoint. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Section 3 | Complete | Sprint 5 Section 3 states that Flutter shall not directly call Qwen3.5-9B, Qwen3.5-4B, Ollama, vLLM, SGLang, llama.cpp, or any model endpoint. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC07 | Acceptance Criteria | Modified | NIS-AC07: No automatic model switching, automatic model failover, runtime routing, load-based model selection, per-feature model assignment, or user-selectable model option shall be introduced | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC08 | Acceptance Criteria | Modified | NIS-AC08: All AI requests shall pass through the Backend, which shall perform authentication, authorisation, privacy checks, visibility checks, data minimisation, purpose limitation, and request validation. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC09 | Acceptance Criteria | Modified | NIS-AC09: The Backend shall provide the model only with the minimum permitted data required for the current approved request. Any inconsistent earlier sponsor or Project Plan wording suggesting comprehensive, broad, or unrestricted data collection is superseded by this requirement. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC10 | Acceptance Criteria | Modified | NIS-AC10: The Backend shall validate expected structure, required values, allowed identifiers, approved candidates, permitted information, and business-rule compliance before accepting model output. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC11 | Acceptance Criteria | Modified | NIS-AC11: Unknown identifiers, unsupported candidates, malformed output, restricted information, privacy violations, visibility violations, and unsupported state changes shall be rejected. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 24 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC12 | Acceptance Criteria | Modified | NIS-AC12: A deterministic Backend fallback shall be used when the model or runtime is unavailable, times out, fails, or returns invalid output. It shall return a controlled deterministic result without automatically activating another model. Core non-AI functions shall remain usable | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 4, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC13 | Acceptance Criteria | Modified | NIS-AC13: Admin shall use the existing Firebase Authentication, and Admin authority shall be verified by the Backend using Firebase custom claims. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 5, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC14 | Acceptance Criteria | Modified | NIS-AC14: Admin assignment shall be performed manually by the Backend or project owner, and the system may support a small set of manually approved Admins. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 5, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC15 | Acceptance Criteria | Modified | NIS-AC15: An authorised Admin shall be able to create, read, update, deactivate, and reactivate Interest content. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 5, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC16 | Acceptance Criteria | Modified | NIS-AC16: Interest Create and Update shall pass entity-specific Backend validation before the operation is accepted. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 5, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC17 | Acceptance Criteria | Modified | NIS-AC17: A deactivated Interest shall remain available to existing historical references but shall not be newly selected, newly assigned to Events, used in future recommendation matching, or included in new AI input. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 5, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC18 | Acceptance Criteria | Modified | NIS-AC18: Admin Interest audit records shall include Admin identity, operation, target entity, target record, timestamp, success or failure, and relevant Interest content and active or deactivated state as before and after values where applicable | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 5, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC19 | Acceptance Criteria | Modified | NIS-AC19: The Sprint design specification shall define protected Backend capabilities for future Disable, Suspend, Delete, and Restore action types without defining or executing final account-state changes. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 5, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC20 | Acceptance Criteria | Modified | NIS-AC20: The design specification shall cover Firebase Authentication, Backend verification of the Admin custom claim, the shared protected internal Admin API scope, restricted script or command-line access, permitted administrative metadata, target-account identification, action-type validation boundaries, audit fields, rejection behaviour, security restrictions, and an explicit no-account-state-change boundary | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 5, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC21 | Acceptance Criteria | Modified | NIS-AC21: Admin may read only the minimum administrative account metadata required for target-account identification, validation, and audit target identification: Firebase UID, account identifier or unique username, username, email address, current account status, and current administrative state. This exception shall not grant access to private Profile information, Check-in records, approximate location, friendship information, AI conversation content, or unrelated application activity. | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 6, 25 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-AC22 | Acceptance Criteria | Added | NIS-AC22: Final account-state execution semantics, including exact grounds, evidence requirements, distinctions between action types, suspension duration, session handling, user notification, appeal, restoration criteria, deletion meaning and effects, data retention, and cascading data handling, remain Deferred and shall not be inferred in this Sprint. 4. Added and Modified Use Cases 4.1 Added or Consolidated Use Cases | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Deferred | Sprint 5 edit.pdf | 6, 10, 26, 29 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Deferred | Source explicitly defers this scope or execution semantics; target DOCX preserves the deferred status. | Design-level requirements are not downgraded merely because executable code is not delivered.

## Sprint 5 FR
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
NIS-FR01 | Functional Requirement | Modified | NIS-FR01 Modified Qwen3.5-9B shall be the primary model for approved project AI functions | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 11, 30 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR02 | Functional Requirement | Added | NIS-FR02 Added Qwen3.5-4B shall be available only as the manually configured development and low-spec alternative model and shall not act as an automatic failover from Qwen3.5-9B | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 11, 30 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR03 | Functional Requirement | Modified | NIS-FR03 Modified Ollama shall be the current local inference runtime, accessed by the Backend through Qwen Local Model Adapter | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 11, 30 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR04 | Functional Requirement | Removed | NIS-FR04 Removed The application shall not require Gemini, Gemini API, Gemini Provider Adapter, Gemini SDK, Gemini credentials, Gemini quota, Gemini billing, or Gemini free-tier availability | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 11, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR05 | Functional Requirement | Modified | NIS-FR05 Modified All AI requests and responses shall pass through the Backend; Flutter shall not directly access any model or inference runtime | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 11, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR06 | Functional Requirement | Modified | NIS-FR06 Modified The Backend shall apply authentication, authorisation, privacy checks, visibility checks, data minimisation, purpose limitation, request construction, output parsing, and output validation | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 11, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR07 | Functional Requirement | Modified | NIS-FR07 Modified The model shall receive only the minimum permitted data and approved results required for the current request. Any inconsistent earlier sponsor or Project Plan wording suggesting comprehensive, broad, or unrestricted data collection shall not apply | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 11, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR08 | Functional Requirement | Modified | NIS-FR08 Modified The Backend shall reject invalid structure, unknown identifiers, unauthorised information, unsupported candidates, and business-rule violations | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 12, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR09 | Functional Requirement | Modified | NIS-FR09 Modified A deterministic Backend fallback shall remain available when model inference fails or produces an invalid result and shall not automatically activate another model | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 12, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR10 | Functional Requirement | Modified | NIS-FR10 Modified Qwen and all inference runtimes shall not directly read, create, update, delete, or query Firestore or another application database | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 12, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR11 | Functional Requirement | Added | NIS-FR11 Added Admin shall use existing Firebase Authentication, manual assignment, and Backend-verified Firebase custom claims | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 12, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR12 | Functional Requirement | Added | NIS-FR12 Added The system shall allow a small manually approved set of Admins and shall prevent Client-side declaration of Admin authority | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 12, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR13 | Functional Requirement | Added | NIS-FR13 Added Authorised Admins shall manage Interest through protected Backend Create, Read, Update, Deactivate, and Reactivate operations | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 12, 31 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR14 | Functional Requirement | Added | NIS-FR14 Added Deactivated Interests shall preserve existing references but shall be excluded from new selection, new Event assignment, future recommendation matching, and new AI input | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 12, 32 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR15 | Functional Requirement | Added | NIS-FR15 Added Interest Create and Update shall pass entity-specific Backend validation before the operation is accepted | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 12, 32 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR16 | Functional Requirement | Added | NIS-FR16 Added Admin audit records shall include Admin identity, operation, target entity, target record, timestamp, success or failure, and before and after values where applicable. Interest-changing operations may record applicable Interest content and active or deactivated state before and after the change. Interest Read does not require before or after values. User Account Administration preparation shall record only the target account identifier, requested action type, relevant current administrative account status or state, preparation result, and success or failure, without claiming an account-state change or copying private user data | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 13, 32 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR17 | Functional Requirement | Added | NIS-FR17 Added The Sprint shall produce a design-level Backend specification for protected User Account Administration preparation covering future Disable, Suspend, Delete, and Restore action types, authorised actors, shared Admin API scope, permitted administrative metadata, validation boundaries, audit fields, rejection behaviour, security restrictions, and an explicit no-account-state-change boundary | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 13, 17, 32, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-FR18 | Functional Requirement | Added | NIS-FR18 Added The design shall define one minimal protected internal Admin API, accessed through a restricted internal script or command-line tool, supporting confirmed Interest Create, Read, Update, Deactivate, and Reactivate operations and protected User Account Administration preparation for future Disable, Suspend, Delete, and Restore action types. Direct Admin database access shall not be permitted. 5.2 Non-Functional Requirements Requirement ID Change Type Requirement | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 13, 17, 32, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3-9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.

## Sprint 5 NFR
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
NIS-NFR01 | Non-functional Requirement | Modified | NIS-NFR01 Modified AI provider abstraction should allow the Backend integration to change inference runtimes without changing Flutter business flows | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 14, 33 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-NFR02 | Non-functional Requirement | Modified | NIS-NFR02 Modified AI-supported functions should remain available through deterministic Backend fallback when local inference is unavailable or invalid, without automatic model failover | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 14, 33 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-NFR03 | Non-functional Requirement | Modified | NIS-NFR03 Modified Model inputs and operational records should minimise sensitive or unrelated user information in accordance with privacy, visibility, purpose-limitation, and Backend-control requirements. Account-administration audit records shall be limited to permitted administrative identifiers, action types, administrative status or state, and preparation results | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 14, 33 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-NFR04 | Non-functional Requirement | Added | NIS-NFR04 Added Admin operations shall be protected against unauthorised use through Firebase Authentication, Backend authorisation, and custom-claim verification | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 14, 33 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-NFR05 | Non-functional Requirement | Added | NIS-NFR05 Added Interest operations and User Account Administration preparation should provide sufficient auditability to identify the Admin, operation, target, time, permitted change or preparation details, and outcome. Before and after values are recorded only where applicable; Read and preparation operations shall not fabricate change values, and private user content shall not be copied into account audit records | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 14, 33 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-NFR06 | Non-functional Requirement | Added | NIS-NFR06 Added Admin authority shall expose only the minimum administrative account metadata required for target identification, validation, preparation, and audit target identification and shall not expose private application content beyond the confirmed administrative scope. 6. Business Rules and Security Boundaries | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 14, 33 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.

## Sprint 5 BR
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
NIS-BR01 | Business Rule | Modified | NIS-BR01 Modified Qwen3.5-9B is the only primary model. Qwen3.5-4B is limited to the manually configured development and low-spec alternative model and is not an automatic failover model | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 15, 34 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR02 | Business Rule | Modified | NIS-BR02 Modified Ollama is the current runtime, while Qwen Local Model Adapter is the Backend abstraction. They are not AI models or databases | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 15, 34 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR03 | Business Rule | Modified | NIS-BR03 Modified vLLM and SGLang may be considered later when a suitable NVIDIA GPU is available; Ollama or llama.cpp may continue where no suitable GPU is available | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 15, 34 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR04 | Business Rule | Modified | NIS-BR04 Modified Every AI request must pass through the Backend, and Flutter cannot directly access the model or runtime | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 15, 34 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR05 | Business Rule | Modified | NIS-BR05 Modified AI cannot directly access the application database, make permission decisions, or execute critical application-state changes. All recommendation candidates, weights, scores, and final ordering shall be generated by the deterministic Backend recommendation algorithm. Qwen may only explain, summarise, or conversationally present Backend-approved recommendation results and shall not add candidates, modify weights, override scores, or change final ordering | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 15, 34 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR06 | Business Rule | Added | NIS-BR06 Added Admins are manually assigned, authenticated through Firebase Authentication, authorised through Backend-verified Firebase custom claims, and limited to a small approved set | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 15, 34 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR07 | Business Rule | Added | NIS-BR07 Added This New Incremental Sprint formally expands the previously confirmed Admin scope from Interest administration only to Interest administration plus protected User Account Administration design | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 15, 34 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR08 | Business Rule | Added | NIS-BR08 Added Interest Delete means deactivation. A deactivated Interest preserves historical references and may be reactivated by an authorised Admin | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 16, 34 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR09 | Business Rule | Added | NIS-BR09 Added Admin may read only Firebase UID, account identifier or unique username, username, email address, current account status, and current administrative state as minimum administrative account metadata for target identification, validation, preparation, and audit target identification. This does not authorise access to private Profile content, Check-in records, approximate location, friendship information, AI conversation content, or unrelated application activity | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 16, 35 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR10 | Business Rule | Added | NIS-BR10 Added Admin cannot modify ordinary Profile content, Going, Interested, Check-in, Privacy, Special Care, Friend Request, friendship, or Persona through the authority defined in this Sprint. Access to minimum administrative account metadata does not create ordinary Profile access | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 16, 35 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR11 | Business Rule | Added | NIS-BR11 Added The Sprint deliverable is a design-level Backend specification for protected User Account Administration preparation. It defines the authorised actors, shared Admin API scope, permitted administrative metadata, validation boundary, audit fields, rejection behaviour, security restrictions, and explicit no-state-change boundary for future Disable, Suspend, Delete, and Restore action types. It does not deliver executable account-state actions | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 16, 35 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-BR12 | Business Rule | Added | NIS-BR12 Added Admin operations require Backend validation and audit logging. Before and after values are required only for operations that actually change Interest content or state. Interest Read does not require before or after values, and User Account Administration preparation uses restricted preparation audit fields rather than actual account-state change values. No approval workflow or general rollback is introduced; Interest reactivation is permitted | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 16, 35 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 7, 8, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.

## Sprint 5 SN
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
NIS-SN01 | Scope Note | Modified | NIS-SN01 Modified The model migration changes the provider, model, runtime, and integration wording only. Existing approved AI-supported business functions remain unchanged within their approved boundaries. Any earlier sponsor or Project Plan wording suggesting comprehensive, broad, or unrestricted data collection is superseded where inconsistent by the latest approved data-minimisation, privacy, visibility, purpose-limitation, and Backend-control requirements. Only the minimum permitted data required for the current approved request or administrative operation may be processed | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 17, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-SN02 | Scope Note | Added | NIS-SN02 Added No automatic model switching, automatic model failover, runtime routing, load-based selection, per-feature assignment, or user model selection is introduced. Qwen3.5-4B is the manually configured development and low-spec alternative model | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 17, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-SN03 | Scope Note | Added | NIS-SN03 Added vLLM, SGLang, and llama.cpp are future deployment options. GPU selection, server specification, containers, orchestration, distributed inference, and production topology remain Deferred | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Deferred | Sprint 5 edit.pdf | 17, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 9, and 10 | Deferred | Source explicitly defers this scope or execution semantics; target DOCX preserves the deferred status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-SN04 | Scope Note | Added | NIS-SN04 Added This package defines design-level requirements, responsibility boundaries, and preparation specifications. It does not claim completed software implementation and does not define API endpoints, routes, methods, request or response schemas, database collections, fields, model installation, deployment scripts, or implementation code | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Deferred | Sprint 5 edit.pdf | 17, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 9, and 10 | Deferred | Source explicitly defers this scope or execution semantics; target DOCX preserves the deferred status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-SN05 | Scope Note | Added | NIS-SN05 Added Exact Interest validation rules, including required fields, format, character limits, whitespace handling, duplicate detection, normalisation, search behaviour, and storage structure, are not defined in this Sprint | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Deferred | Sprint 5 edit.pdf | 18, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 9, and 10 | Deferred | Source explicitly defers this scope or execution semantics; target DOCX preserves the deferred status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-SN06 | Scope Note | Added | NIS-SN06 Added This Sprint formally expands the Admin scope only from Interest administration to Interest administration plus protected User Account Administration design and preparation. User-account action grounds, evidence requirements, distinctions between Disable and Suspend, suspension duration, login blocking, current-session handling, warning stages, user notification, appeal, restoration criteria, restorable states, Delete meaning, logical or physical deletion, Firebase Authentication deletion, delete confirmation, deletion effects, data retention, cascading data handling, content ownership transfer, permanent-delete timing, recovery | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 10, 18, 29, 36 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-SN07 | Scope Note | Added | NIS-SN07 Added No Admin UI, dashboard, or mobile page is required. Any earlier Project Plan reference to an Admin prototype, Admin configuration interface, dashboard, mobile page, or complete Admin UI workflow is Deferred and is not part of the current New Incremental Sprint. The current scope is limited to Backend design and specification for protected administration through one shared minimal protected internal Admin API used by a restricted internal script or command-line tool | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Deferred | Sprint 5 edit.pdf | 18, 37 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 9, and 10 | Deferred | Source explicitly defers this scope or execution semantics; target DOCX preserves the deferred status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-SN08 | Scope Note | Modified | NIS-SN08 Modified Existing Check-in, Friends Activity, Special Care, Friend Search, Homepage, Persona, Going, and Interested requirements remain frozen. Core Event workflows and deterministic Recommendation logic remain frozen except for the approved direct effect that a deactivated Interest preserves existing references but cannot be newly assigned to Events, used in future recommendation matching, or included in new AI input. Where earlier Project Plan wording conflicts with the latest approved Sprint 5 Privacy flow, the latest Sprint 5 decision takes precedence: initial Accept saves Public, initial Reject saves Private, either choice permi | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 19, 37 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 3, 9, and 10 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.

## Sprint 5 UC
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
NIS-UC01 | Use Case | Modified | NIS-UC01 — Process a Backend-Controlled Qwen Request Primary Actor: User Supporting Components: Backend, Qwen Local Model Adapter, Ollama, Qwen3.5-9B, or Qwen3.5-4B as the manually configured development and low-spec alternative model Preconditions The user is authenticated where required by the existing feature. The request belongs to an approved AI-supported purpose. The Backend can determine the permitted data and candidates for the request. Trigger The user initiates an existing approved AI-supported function. Main Flow 1. Flutter sends the authenticated request to the Backend. 2. The Backend identifies the approved request purpose. 3 | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 6, 26 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-UC02 | Use Case | Modified | NIS-UC02 — Manage Interest Content Primary Actor: Admin Preconditions The Admin is authenticated through Firebase Authentication. The Backend verifies the Admin custom claim. The Admin uses a restricted internal script or command-line tool that calls the shared protected internal Admin API. Trigger The Admin submits an Interest-management operation. Main Flow — Read 1. The Admin requests to view existing Interest content. 2. The Backend verifies authentication and Admin authority. 3. The Backend retrieves the permitted Interest records. 4. The Backend returns the permitted active and deactivated Interest records through the restricted adm | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 7, 27 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.
NIS-UC03 | Use Case | Modified | NIS-UC03 — Prepare a User Account Administration Operation Primary Actor: Admin Preconditions The Admin is authenticated through Firebase Authentication. The Backend verifies the Admin custom claim. The target account can be identified using only permitted minimum administrative account metadata: Firebase UID, account identifier or unique username, username, email address, current account status, and current administrative state. The design specifies that requests use the same shared protected internal Admin API defined for confirmed Interest operations. Trigger The Admin submits a design-level account-administration preparation request | Sprint 5 | Sprint 4 Gemini/provider arrangement or newly added Sprint 5 Admin scope | Final | Sprint 5 edit.pdf | 9, 28 | 04_Sprint_5_AI_and_Admin_Report_EN_Final.docx | Sections 6, 8, and 9 | Complete | Target DOCX contains the required content with correct Sprint 5 status. | Design-level requirements are not downgraded merely because executable code is not delivered.

## Coverage Gaps
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
GAP-00 | Coverage Gap | QA | No open coverage gap remained after extracting source IDs, validating concrete summaries, and matching target DOCX sections. | All | All source PDFs and generated DOCX | Final | All source PDFs | Checked by automated extraction | All DOCX and XLSX | QA | Complete | Generated after actual validation; not pre-seeded.

## QA Checks
Requirement ID | Requirement Type | Change Type | Exact Requirement Summary | Sprint Introduced | Prior Requirement / Modified Source | Current Status | Source PDF | Exact PDF Page | Target DOCX | Target Section | Coverage Result | Evidence | Notes
QA-01 | QA Check | QA | All expected formal output files are present. | All |  | Final | Generated outputs | N/A | All | Final QA | Complete | File existence check passed.
QA-02 | QA Check | QA | Forbidden internal terms and generic source-reference summaries were searched. | All |  | Final | Generated outputs | N/A | All | Final QA | Complete | Search excludes required column heading Current Status.
QA-03 | QA Check | QA | All Word sections use A4 portrait page setup with 1.8 cm margins. | All |  | Final | Generated DOCX | N/A | All DOCX | Final QA | Complete | Section geometry audit passed.